## Blad1
Name Asset: | Priority: | Deadline: | General Information: | Amount: | Done: | TOTAL TIME SPENT: | Made by: | Estimated Time: | High Priority | [X] = NOT DONE
StyleGuide | High Priority | 2017-02-07 | Reference Material | (0/1) | [+] | 4:30 Hour(s) | GROEP | 1:30 Hour(s) | Medium Priority | [+] = DONE
Storyline | High Priority | 2017-02-05 | Backstory | (1/1) | [+] | 1:00 Hour(s) | GROEP | 3:00 Hour(s) | Low Priority
Concept_Character_Joey | High Priority | 2017-02-10 | Concept persoon | (1/1) | [+] | 1:00 Hour(s) | Joey | 2:30 Hour(s)
Concept_Character_Thomas | High Priority | 2017-02-10 | Concept persoon | (1/1) | [+] | 1:00 Hour(s) | Thomas | 2:30 Hour(s)
Concept_Character_Guy | High Priority | 2017-02-10 | Concept persoon | (1/1) | [+] | 1:00 Hour(s) | Guy | 2:30 Hour(s)
Spr_Warmthmeter_Empty | Medium Priority | 2017-02-27 | Spr lege meter | (1/1) | [+] | 0:45 Hours(s) | Thomas | 0:30 Hour(s)
Spr_Warmthmeter_Fill | Medium Priority | 2017-02-27 | spr gevulde meter | (1/1) | [+] | 0:45 Hour(s) | Thomas | 0:30 Hour(s)
Spr_Interface_Background | Medium Priority | 2017-02-27 | Achtergrond keuze menu | (1/1) | [+] | 1:00 Hour(s) | Joey | 1:00 Hour(s)
Spr_Button | Medium Priority | 2017-02-27 | Sprite Button | (1/1) | [+] | 0:20 Hour(s) | Joey | 1:00 Hour(s)
Class_AI | Medium Priority | 2017-02-07 | Following AI | (1/1) | [+] | 1:40 Hour(s) | Guy | 3:00 Hour(s)
Class_Subtitle | High Priority | 2017-02-27 | Speach tekst | (0/1) | [X] | 2:00 Hour(s) | Guy | 3:00 Hour(s)
Class_Movement | High Priority | 2017-02-27 | Lets player move | (0/1) | [X] | 0:15 Hour(s) | Guy | 1:30 Hour(s)
Class_GameManager | High Priority | 2017-02-27 | Core GameMechanic Script | (0/1) | [X] | 3:00 Hour(s) | Guy | 2:30 Hour(s)
SCE_Joey | High Priority | 2017-04-10 | Scene Joey | (0/1) | [X] |  | Joey | 5:00 Hour(s)
SCE_Guy | High Priority | 2017-04-10 | Scene Guy | (0/1) | [X] |  | Guy | 5:00 Hour(s)
SCE_Thomas | High Priority | 2017-04-10 | Scene Thomas | (0/1) | [X] |  | Thomas | 5:00 Hour(s)
Char_Rig_Thomas | High Priority | 2017-03-06 | Character Model Rig | (0/1) | [X] |  | Thomas | 4:00 Hour(s) for Test, 2:00 Hour(s) for actual
Char_Rig_Guy | High Priority | 2017-03-06 | Character Model Rig | (0/1) | [X] |  | Guy | 4:00 Hour(s) for Test, 2:00 Hour(s) for actual
Char_Rig_Joey | High Priority | 2017-03-06 | Character Model Rig | (0/1) | [X] |  | Joey | 4:00 Hour(s) for Test, 2:00 Hour(s) for actual
Char_Model_Joey_Final | High Priority | 2017-02-24 | Character Models Itself | (0/1) | [X] |  | Joey | 12:00 Hour(s)
Char_Model_Thomas_Final | High Priority | 2017-02-24 | Character Models Itself | (0/1) | [X] |  | Thomas | 12:00 Hour(s)
Char_Model_Guy_Final | High Priority | 2017-02-24 | Character Models Itself | (0/1) | [X] |  | Guy | 12:00 Hour(s)
UVW_Char_Joey | High Priority | 2017-03-13 | Character Models UVWrap | (0/1) | [X] |  | Joey | 4:00 Hour(s)
UVW_Char_Thomas | High Priority | 2017-03-13 | Character Models UVWrap | (0/1) | [X] |  | Thomas | 4:00 Hour(s)
UVW_Char_Guy | High Priority | 2017-03-13 | Character Models UVWrap | (0/1) | [X] |  | Guy | 4:00 Hour(s)
TEX_Char_Joey | High Priority | 2017-03-27 | Character Textures | (0/1) | [X] |  | Joey | 8:00 Hour(s)
TEX_Char_Thomas | High Priority | 2017-03-27 | Character Textures | (0/1) | [X] |  | Thomas | 9:00 Hour(s) (IVB met details)
TEX_Char_Guy | High Priority | 2017-03-27 | Character Textures | (0/1) | [X] |  | Guy | 8:00 Hour(s)
AUD_CharacterSpeach(s) | Low Priority | Optional | Speach | (0/25) | [X] |  | GROEP | 2:00 Hour(s)
OBJ_SneeuwPop | Low Priority | Optional | Scenery | (0/1) | [X] |  | Guy | 1:00 - 1:30 hour(s)